## Q3-2021
COMPONENT
Week | Backend | Frontend
2021-KW26 | Set up Source Control Implement basic build process using GitHub Actions Test build process locally | Implement build process
2021-KW27 | Implement build process on Azure Pipelines
2021-KW28 | Test continuous delivery | Test continuous delivery
2021-KW29 | API that returns no data
2021-KW30 |  | Connects to an API
2021-KW31
2021-KW32
2021-KW33 |  | Deploy AZ AppService
2021-KW34 |  | Test Flask ML API
2021-KW35
2021-KW36 | QA-Cushion
2021-KW37
Goals per Component | Backend | Frontend
| ML API | Deploy on Azure
| Logging | Python/Flask
Use of Github Actions
Use of Azure Pipelines