## Q3-2021
COMPONENT
Week | Implementation | Project Management
2021-CW18 | Create GitHub repo with scaffolding code | Create project plan
Create a trello board
2021-CW19 | Implement basic build process using GitHub Actions | Take screenshots and maintain README
Test build process locally
2021-CW20
2021-CW21
| Deploy AppService on Azure | Create architectural diagram and maintain README
| Test AppService | Add full instructrutions to README on how to run the code
Implement build process on Azure Pipelines
2021-CW22 | Test continuous delivery
2021-CW23
2021-CW24
2021-CW25
2021-CW26 |  | Record demo video
Finalize README
First submit of project
Goals per Component | Backend | Frontend
| Use of Github Actions | Deploy WebApp on Azure
Use of Azure Pipelines